## Defects
Sitters4Me Defect and Observation Log
Defect ID | Source | Summary | Severity | Priority | Status | Evidence | Recommendation
OBS-001 | Static lint | Lint reports 21 errors and 69 warnings in supplied snapshot. | High | P0 | Open | npm run lint, 2026-07-27 | Resolve errors before release candidate; triage warnings.
OBS-002 | Static lint | Session restore source references a FileSystem API reported unavailable by lint. | High | P0 | Open | app/index.tsx lint result | Validate and remediate against Expo SDK 54; verify cold restore on devices.
OBS-003 | Source scope | Authentication backend referenced by requirements is not in supplied snapshot. | Medium | P1 | Open | Source inventory | Provide backend baseline and API contract for IV&V.